## Confirmed barriers
Internal Name | Barrier ID (Crossing ID) | Watercourse Name | Road Name | Easting | Northing | Zone | Barrier Type | Barrier Owner | Number of Downstream Barriers | Assessment Type/Assessment Step Completed | Date of assesment | Passability status | Partial passability notes | Upstream habitat Quality | Total Habitat Gain (km) | Habitat Gain (km) - spawning | Habitat Gain (km) - rearing | Constructability | Estimated cost | cost-benefit Ratio | Priority | Next Steps | Timeline for Next Steps | Lead for Next Steps | Others involved in next steps | Reason | Notes
|  | Model | Model |  |  |  | Model |  | Model |  | Model | Model |  |  | Model | Model | Model
Note on M1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: would need to be split up until the same number of columns as there are species/guilds
Note on Q1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: this would need to be avg gain for each species
Note on R1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: this would need to be avg gain for each species
Note on Y1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there value in having a column for others involved that aren't leading?

## Categories
Column | Categories
Next Steps
Engage with barrier owner
Bring barrier to regulator
Commission engineering designs
Remove
Replace
Leave until end of life cycle
identify barrier owner
Engage in public consultation
Fundraise
Constructability
Difficult
Moderate
Easy
Upstream habitat quality
High
Medium
Low
N/A or unassessed
Assessment completed
Informal assessment
Barrier assessment
Habitat confirmation
Detailed habitat investigation
Engineering design
Note on A12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: could consider adding these categories
Note on A21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For NS it makes sense to say Formal vs Informal assessment completed, but what happens in BC when a barrier assessment is completed one year and then the habitat assessment the next visit, is there the possibility of having two categories represented here?
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Perhaps we should consider renaming this to "passability assessment" to be more in line with our terminology (using barrier only if/when its been assessed as one) Reply: I guess this is likely fine given it is on the confirmed barriers list, so maybe moot point.. but will leave comment there in case anyone agrees